## Sheet1
No | Issues | Status | Date of Resolution | Date of Detection | Detected by | Resolved by
1 | Database Connectivity | Solved | 2016-07-19 | 2016-07-01 | Akanksha | Akanksha
2 | No validations for sign up page for password and confirm password fields | solved | 2016-07-23 | 2016-07-13 | Smitha | Akanksha
3 | Login screen | solved | 2016-07-23 | 2016-07-15 | Smitha | Akanksha
4 | Logout Option not available | solved | 2016-07-27 | 2016-07-22 | Akanksha | Akanksha
5 | It was throwing exception when we click on the compare button and was not leading to the next page | solved | 2016-07-28 | 2016-07-26 | Smitha | Smitha
6 | On clicking of the Continue button we are getting navigated but the drop down was empty | solved | 2016-08-04 | 2016-07-29 | Smitha | Akanksha
7 | the row Contact number of the booking table was not getting inserted | solved | 2016-08-07 | 2016-08-05 | Akanksha | Smitha
8 | Rate Option not working and inserting values | solved | 2016-08-09 | 2016-08-09 | Akanksha | Smitha